## Sheet1
Nama | : TRIWAHYU PAMUNGKAS PRIBADI
Jabatan | : WEB & ANDROID DEVELOPER
No | Date | Req Date | Deadline | Start Date | Finish Date | Work Time | End Date | Server | Modul | Menu | Description | Status | PIC
1 | 2021-01-04 | 2021-01-04 | 1 Day | 2021-01-04 | 2021-01-04 | 1 Day | 2021-01-04 | API SFA | - | - | Revisi: 1). Login sebagai HOR/TSS/TAO dll muncul data inbox yg dikirim user lain (nanti tampilkan sesuai user yg create saja, kecuali admin dk, full akses) | DONE | FIRZA
[8 empty] | DKDS | SFA | Sharing Inbox | Revisi: 1). Ganti filter minta tolong ceklist all nya dikosongi juga seperti checklist yg di salesman | DONE | FIRZA
[11 empty] | 2). Yang sudah dibaca dikasih warna lain tulisannya biar terlihat perbedaannya | DONE | FIRZA
[11 empty] | 3). Muncul error saat klik save dalam kondisi kode salesman tidak tampil | DONE | FIRZA
[11 empty] | 4). Jika ada kolom yang masih belum terisi kenapa nama salesman dilist menjadi hilang | DONE | FIRZA
[8 empty] | API SFA & DKDS |  | Report Generator Code | Revisi: 1). Tambah export to xls | DONE | FIRZA
[10 empty] | Report KM Awal - Akhir | Revisi: 1). Tambah print dan export to xls | DONE | FIRZA
[11 empty] | 2). Jika nation dipilih, filter lainnya masih not found | DONE | FIRZA
[11 empty] | 3). Tampilan foto disesuaikan, jangan terlalu besar | DONE | FIRZA
[11 empty] | 4). Lokasi start dan akhir tidak sesuai karena posisi saat start dikantor tetapi dapat pinnya di dukuh kupang barat | DONE | FIRZA
[10 empty] | Report Analisa Kunjungan Salesman | Revisi: 1). Jika filter tipe operasi sales diisi maka salesman yg ditampilkan hanya sales tipe tersebut | DONE | FIRZA
2 | 2021-01-05 | 2021-01-05 | 1 Day | 2021-01-05 | 2021-01-05 | 1 Day | 2021-01-05 | API SFA | REPORT | Report Analisa Kunjungan Salesman | Query Export to pdf dan excel, export show order | DONE | FIRZA
[8 empty] | DKDS | SFA |  | Revisi: 1). Data diurutkan sesuai tanggal transaksinya (ascending), kemudian kasih hari nya juga, <<hari>>,<<tanggal>> <<jumlah salesman yg transaksi hari itu>> | DONE | FIRZA
[11 empty] | 2). Revisi nilai call plan, actual call, ipt, ec | DONE | FIRZA
[11 empty] | 3). Di bagian header nama salesman itu butuh kolom juga untuk jam masuk, selesai, waktu tempuh (nanti dapatnya dari jam start visit sama jam end visit) | DONE | FIRZA
[11 empty] | 4). Export show order | DONE | FIRZA
3 | 2021-01-06 | 2021-01-06 | 1 Day | 2021-01-06 | 2021-01-06 | 1 Day | 2021-01-06 | DKDS | SFA | Report Penjualan Inquiry | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Penjualan Inquiry Realisasi | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Data Control | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report User Access | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Stock Cabang | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Transaksi Sample | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Monitoring Credit Limit | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Return Summary | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Return Detail | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Top N | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Kompetitor Activity | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Kompetitor Market Share | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Kompetitor Availability | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Kompetitor New Product | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Target vs Realization | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Exception Sales | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Exception Non Permanent Journey Plan | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Exception Order Out of Area | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Crosschecking Cashier vs Salesman per Salesman | Form report, query hierarki, frontend, dll | DONE | FIRZA
[10 empty] | Report Analisa Kunjungan Salesman | Form report, query hierarki, frontend, dll | DONE | FIRZA
4 | 2021-01-07 | 2021-01-07 | 1 Day | 2021-01-07 | 2021-01-07 | 1 Day | 2021-01-07 | API SFA | REPORT | Report Penjualan Inquiry Realisasi | Query data penjualan inquiry realisasi | IN REVIEW | FIRZA
[10 empty] | Report Penjualan Inquiry | Query data penjualan inquiry | IN REVIEW | FIRZA
[10 empty] | Report Data Control | Query search salesman yang melakukan absensi by periode | IN PROGRES | FIRZA
5 | 2021-01-08 | 2021-01-08 | 1 Day | 2021-01-08 | 2021-01-08 | 1 Day | 2021-01-08 | API SFA | REPORT | Report Data Control | Query search salesman yang melakukan absensi by periode | IN REVIEW | FIRZA
[10 empty] | Report Stock Cabang | Query data stok cabang | IN PROGRES | FIRZA
6 | 2021-01-11 | 2021-01-11 | 1 Day | 2021-01-11 | 2021-01-11 | 1 Day | 2021-01-11 | API SFA | TRANSAKSI | - | API kirim data retur produk ke server | IN REVIEW | DANI
7 | 2021-01-12 | 2021-01-12 | 1 Day | 2021-01-12 | 2021-01-12 | 1 Day | 2021-01-12 | API SFA | TRANSAKSI | - | API kirim data produk sample ke server | IN REVIEW | DANI
[8 empty] | DKDS | SFA | Report Analisa Kunjungan Salesman | Revisi: 1). Tambah header region, titik, distributor dan tanggal di view data | DONE | FIRZA
[11 empty] | 2). Merapikan tampilan report analisa kunjungan | DONE | FIRZA
[10 empty] | Report Data Control | Revisi: 1). Tambah header region, titik, distributor dan tanggal di view data | DONE | FIRZA
[10 empty] | Laporan Dinding | Revisi: 1). Tambah header region, titik, distributor dan tanggal di view data | DONE | FIRZA
[10 empty] | Report Unfullfillment | Revisi: 1). Tambah header region, titik, distributor dan tanggal di view data | DONE | FIRZA
[10 empty] | Report Penjualan Inquiry Realisasi | Revisi: 1). Tambah header region, titik, distributor dan tanggal di view data | DONE | FIRZA
[10 empty] | Report KM Awal - Akhir | Revisi: 1). Tambah header region, titik, distributor dan tanggal di view data | DONE | FIRZA
8 | 2021-01-13 | 2021-01-13 | 1 Day | 2021-01-13 | 2021-01-13 | 1 Day | 2021-01-13 | API SFA | REPORT | Report Analisa Kunjungan Salesman | Revisi: 1). Error divisi by zero (kurang filter tanggal saat menampilkan detail outlet) | DONE | FIRZA
[11 empty] | 2). Export data analisa dalam format excel | IN REVIEW | FIRZA
[10 empty] | Report Stock Outlet | API query data stock outlet | IN REVIEW | FIRZA
[9 empty] | TRANSAKSI | - | Revisi: 1). Generate code error format pada saat simpan header | DONE | DANI
[11 empty] | 2). Error format kirim gambar pada saat send data produk sample ke server | DONE | DANI
9 | 2021-01-14 | 2021-01-14 | 1 Day | 2021-01-14 | 2021-01-14 | 1 Day | 2021-01-14 | API SFA | REPORT | Report Transaksi Sample | 1). API query data product sample | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
[10 empty] | Report Data Control | Revisi: 1). Summary percentage penggunaan device salesman by periode | IN REVIEW | FIRZA
[10 empty] | Report Stock Outlet | Export to excel | IN REVIEW | FIRZA
[10 empty] | Report Unfullfillment | Revisi: 1). Revisi header report to excel | IN REVIEW | FIRZA
[9 empty] | TRANSAKSI | - | Revisi: 1). Error validasi pada saat simpan detail retur | DONE | DANI
10 | 2021-01-18 | 2021-01-18 | 1 Day | 2021-01-18 | 2021-01-18 | 1 Day | 2021-01-18 | API SFA & DKDS | REPORT | Report Return Summary | 1). API query data retur | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
[10 empty] | Report Return Detail | 1). API query data retur | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
[10 empty] | Report Data Control | Export to excel | IN REVIEW | FIRZA
11 | 2021-01-19 | 2021-01-19 | 4 Day | 2021-01-19 | 2021-01-22 | 1 Day | 2021-01-22 | API SFA & DKDS | REPORT | Report Top N | API query produk by value | IN PROGRES | FIRZA
12 | 2021-01-20 | 2021-01-19 | 4 Day | 2021-01-19 | 2021-01-22 | 1 Day | 2021-01-22 | API SFA & DKDS | REPORT | Report Top N | 1). API query produk by value | IN REVIEW | FIRZA
[11 empty] | 2). Query show data transaksi 3 bulan terakhir | IN PROGRES | FIRZA
13 | 2021-01-21 | 2021-01-19 | 4 Day | 2021-01-19 | 2021-01-22 | 1 Day | 2021-01-22 | API SFA & DKDS | REPORT | Report Top N | 1). Query show data transaksi 3 bulan terakhir | IN REVIEW | FIRZA
[11 empty] | 2). API query produk by Qty | IN REVIEW | FIRZA
[11 empty] | 3). API query customer by value | IN REVIEW | FIRZA
[11 empty] | 4). API query customer by Qty | IN REVIEW | FIRZA
|  | 2021-01-21 | 2 Day | 2021-01-21 |  |  | 2021-01-21 |  |  | Report Monitoring Credit Limit | 1). API query show kredit limit, sisa limit, persentasi remaining and used kredit limit | IN PROGRES | FIRZA
[11 empty] | 2). Export to excel | IN PROGRES | FIRZA
14 | 2021-01-22 | 2021-01-21 | 2 Day | 2021-01-21 | 2021-01-22 | 1 Day | 2021-01-22 | API SFA & DKDS | REPORT | Report Monitoring Credit Limit | 1). API query show kredit limit, sisa limit, persentasi remaining and used kredit limit | IN REVIEW | FIRZA
|  | 2021-01-22 | 1 Day | 2021-01-22 | [6 empty] | 2). Export to excel | IN REVIEW | FIRZA
[10 empty] | Report Transaksi TO | 1). API query data transaksi salesman TO | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
15 | 2021-01-25 | 2021-01-25 | 1 Day | 2021-01-25 | 2021-01-25 | 1 Day | 2021-01-25 | API SFA | TRANSAKSI | Cost Salesman | API send data apk ke server SFA | DONE | DANI
|  |  | 2 Day |  | 2021-01-26 |  | 2021-01-26 | API SFA & DKDS | REPORT | Report Cost Salesman | 1). API query data cost salesman | IN PROGRES | FIRZA
[11 empty] | 2). Export to excel | IN PROGRES | FIRZA
[10 empty] | Report Monitoring Daily Sales / Customer | 1). API query data monitoring daily salesman/customer | IN PROGRES | FIRZA
16 | 2021-01-26 | 2021-01-25 | 2 Day | 2021-01-25 | 2021-01-26 | 1 Day | 2021-01-26 | API SFA & DKDS | REPORT | Report Monitoring Daily Sales / Customer | 1). API query data monitoring daily salesman/customer | IN REVIEW | FIRZA
|  | 2021-01-26 |  | 2021-01-26 | [5 empty] | Report Cost Salesman | 1). API query data cost salesman | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
[8 empty] | API SFA | TRANSAKSI | Cost Salesman | Revisi update data cost salesman | DONE | FIRZA
[5 empty] | 2021-01-27 |  | 2021-01-27 |  |  | Delivery Dropping | API send data dropping ke server SFA | IN PROGRES | DANI
17 | 2021-01-27 | 2021-01-27 | 1 Day | 2021-01-27 | 2021-01-27 | 1 Day | 2021-01-27 | API SFA & DKDS | REPORT | Report Target vs Realization | 1). API query data target vs realization | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
|  | 2021-01-28 | 2 Day | 2021-01-28 | 2021-01-28 |  | 2021-01-28 |  |  | Report Dropping | 1). API query data dropping | IN PROGRES | FIRZA
[11 empty] | 2). Export to excel | IN PROGRES | FIRZA
[8 empty] | API SFA | TRANSAKSI | - | API sync data dropping ketika sales melakukan sync data master melalui APK | IN PROGRES | FIRZA
18 | 2021-01-28 | 2021-01-27 | 2 Day | 2021-01-27 | 2021-01-28 | 1 Day | 2021-01-28 | API SFA & DKDS | REPORT | Report Dropping | 1). API query data dropping | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
[8 empty] | API SFA | TRANSAKSI | Delivery Dropping | 1). API sync data dropping ketika sales melakukan sync data master melalui APK | DONE | DANI
[11 empty] | 2). Update order stok dropping | DONE | DANI
|  | 2021-01-28 |  | 2021-01-28 | 2021-01-29 |  | 2021-01-29 | API SFA & DKDS |  | Real Order | 1). Show list RO SFA, View detail RO SFA | IN REVIEW | FIRZA
[11 empty] | 2). Post data real order SFA ke server DKDS | IN PROGRES | FIRZA
19 | 2021-01-29 | 2021-01-28 | 2 Day | 2021-01-28 | 2021-01-29 | 1 Day | 2021-01-29 | API SFA & DKDS | TRANSAKSI | Real Order | Post data real order SFA ke server DKDS | IN REVIEW | FIRZA
|  | 2021-01-29 | 1 Day |  |  |  |  | API SFA |  | Cost Salesman | Revisi max length code cost salesman di server SFA | DONE | DANI
20 | 2021-02-01 | 2021-02-01 | 1 Day | 2021-02-01 | 2021-02-01 | 1 Day | 2021-02-01 | API SFA & DKDS | TRANSAKSI | Real Order | Revisi: 1). Filter di list RO SFA, ada kendala ketika ada mapping data dari server DKDS dan SFA | IN REVIEW | FIRZA
[11 empty] | 2). Logs query | IN REVIEW | FIRZA
|  |  | 2 Day |  | 2021-02-01 |  | 2021-02-01 |  | REPORT | Report Exception Sales | 1). API query target amount, inquiry amount dan achiev dalam satu periode | IN REVIEW | FIRZA
[11 empty] | 2). API query data penjualan per periode group by tanggal dalam periode tsb. | IN REVIEW | FIRZA
[11 empty] | 3). Export xls dan pdf | IN PROGRES | FIRZA
21 | 2021-02-02 | 2021-02-01 | 2 Day | 2021-02-01 | 2021-02-02 | 1 Day | 2021-02-02 | API SFA & DKDS | REPORT | Report Exception Sales | Export xls dan pdf | IN REVIEW | FIRZA
|  | 2021-02-02 | 1 Day | 2021-02-02 |  |  |  | API SFA |  | Report Analisa Kunjungan Salesman | Error division by zero saat export xls dan pdf | IN REVIEW | FIRZA
22 | 2021-02-03 | 2021-02-03 | 1 Day | 2021-02-03 | 2021-02-03 | 1 Day | 2021-02-03 | API SFA | TRANSAKSI | Invoice | API untuk create tarikan invoice dari DKDS pada saat verifikasi invoice dari menu APK | DONE | DANI
[8 empty] | API SFA & DKDS | MASTER | Master Kompetitor Brand | API untuk create, update, delete data | IN REVIEW | FIRZA
[10 empty] | Master Kompetitor Sub Brand | API untuk create, update, delete data | IN REVIEW | FIRZA
[10 empty] | Master Kompetitor Activity | API untuk create, update, delete data | IN REVIEW | FIRZA
[10 empty] | Master Kompetitor Product | API untuk create, update, delete data | IN REVIEW | FIRZA
23 | 2021-02-04 | 2021-02-04 | 1 Day | 2021-02-04 | 2021-02-04 | 1 Day | 2021-02-04 | API SFA & DKDS | REPORT | Report Unfullfillment | Revisi: 1). Ketika filter distributor diisi distributor A, data distributor B ikut muncul (kurang filter distributor_code di left joinnya) | IN REVIEW | FIRZA
[11 empty] | 2). Export to pdfnya masih belum urut datanya (urutkan by kode sales, kode outlet, reason, tgl) | IN REVIEW | FIRZA
[10 empty] | Report KM Awal - Akhir | Revisi: 1). Export xls dikasih header seperti tampilan di web | IN REVIEW | FIRZA
[11 empty] | 2). Print PDF tampilanya dirapikan seperti tampilan di web | IN REVIEW | FIRZA
[11 empty] | 3). Jika ganti filter region, filter area dan distributor di null kan saja, biar tidak error saat load data | IN REVIEW | FIRZA
[11 empty] | 4). Jika nation dipilih all nation, kemudian distributor diisi datanya tidak tampil | IN REVIEW | FIRZA
[11 empty] | 5). Belum ada kolom titik | IN REVIEW | FIRZA
[11 empty] | 6). Jika ganti filter nation yg terclear hanya kolom region harusnya sampai area dan distributor | IN REVIEW | FIRZA
[10 empty] | Report Analisa Kunjungan Salesman | Revisi: 1). Jumlah salesman yang transaksi per hari belum ditampilkan | IN REVIEW | FIRZA
[8 empty] | DKDS | MASTER | Master Kompetitor Product | Revisi: 1). Autocomplete data produk ambil dari DKDS | IN REVIEW | FIRZA
[11 empty] | 2). Get product flavour dari DKDS | IN REVIEW | FIRZA
[8 empty] | API SFA |  |  | 3). Get subbrand kompetitor dari SFA | IN REVIEW | FIRZA
24 | 2021-02-05 | 2021-02-05 | 1 Day | 2021-02-05 | 2021-02-05 | 1 Day | 2021-02-05 | API SFA | TRANSAKSI | - | Tambah kolom sales_code dan sales_name di semua table transaksi dan route active | IN REVIEW | FIRZA
[10 empty] | - | Simpan sales_code, sales_name, sales_type, di semua table transaksi dan route active | IN REVIEW | FIRZA
[9 empty] | REPORT | All Report | Revisi ketika ambil data sales_code dan sales_name (tidak perlu left join lagi karena di masing2 table transaksi sudah ada kolom sales_code dan sales_name) | IN REVIEW | FIRZA
[9 empty] | AR | - | API kirim data invoice verifikasi ke server SFA | DONE | DANI
[8 empty] | DKDS | SFA | Sharing Inbox | Revisi: 1). Tampilkan filter jumlah yang ingin ditampilkan | IN REVIEW | FIRZA
[11 empty] | 2). Login sebagai admindk, semua data di munculkan | IN REVIEW | FIRZA
[11 empty] | 3). Jika ganti filter, hilangkan centangan checkbox | IN REVIEW | FIRZA
25 | 2021-02-08 | 2021-02-08 | 1 Day | 2021-02-08 | 2021-02-08 | 1 Day | 2021-02-08 | API SFA | TRANSAKSI | Data Invoice | Revisi: 1). Internal Server Error","message":"ERROR CREATE AR TAGIHAN: CREATED AT MUST BE AN INTEGER., UPDATED AT MUST BE AN INTEGER | DONE | DANI
[11 empty] | 2). ERROR CREATE AR TAGIHAN: THE COMBINATION \"TG20210205001\"-\"LPDMT002\" OF NO DOC AND DISTRIBUTOR CODE HAS ALREADY BEEN TAKEN | DONE | DANI
[8 empty] | DKDS | SFA | All Report | Revisi: 1). Export PDF dikasih footer untuk halaman dan tanggal tarik | IN REVIEW | FIRZA
[10 empty] | Report Analisa Kunjungan Salesman | Revisi: 1). Tombol terkait maps masih belum bisa dipakai | IN REVIEW | FIRZA
[11 empty] | 2). Untuk waktu tempuhnya dikasih hari juga seperti ssmdk | IN REVIEW | FIRZA
[8 empty] | API SFA | - | - | API sync data master kompetitor (brand, subbrand, product dan activity) ke APK | DONE | FIRZA
|  |  | 2 Day |  | 2021-02-09 |  | 2021-02-09 | API SFA & DKDS | REPORT | Report Collection | API data collection, API get data tagihan | IN PROGRES | FIRZA
26 | 2021-02-09 | 2021-02-08 | 2 Day | 2021-02-08 | 2021-02-09 | 1 Day | 2021-02-09 | API SFA & DKDS | REPORT | Report Collection | 1). API data collection, API get data tagihan | PENDING (belum ada data, masih in progress dari APK) | FIRZA
[8 empty] | API SFA | TRANSAKSI | - | API Simpan data latitude dan longitude outlet pada saat start visit (jika masih kosong) | DONE | FIRZA
|  | 2021-02-09 | 1 Day | 2021-02-09 |  |  |  | API SFA & DKDS | REPORT | Report Exception Non Permanent Journey Plan | 1). API call plan, % call, % non route, % non visit per salesman | IN REVIEW | FIRZA
[11 empty] | 2). API call plan, % call, % non route, % non visit per tanggal | IN REVIEW | FIRZA
[11 empty] | 3). API mencari waktu tempuh dan waktu per outlet untuk non rute | IN REVIEW | FIRZA
[11 empty] | 4). Export to excel dan PDF | IN REVIEW | FIRZA
27 | 2021-02-10 | 2021-02-10 | 1 Day | 2021-02-10 | 2021-02-10 | 1 Day | 2021-02-10 | API SFA | TRANSAKSI | - | Revisi: 1). Kirim data collection dari APK ke SFA server | DONE | DANI
[11 empty] | 2). Error unknown property pada saat upload data kunjungan | DONE | DANI
|  | 2021-02-08 | 2 Day | 2021-02-08 |  |  |  | API SFA & DKDS | REPORT | Report Collection | 1). API data collection, API get data tagihan | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
28 | 2021-02-11 | 2021-02-11 | 1 Day | 2021-02-11 | 2021-02-11 | 1 Day | 2021-02-11 | API SFA & DKDS | SFA | ALL MENU SFA | Create user access menu untuk menyimpan user yang mengakses menu SFA | IN REVIEW | FIRZA
|  |  | 2 Day |  | 2021-02-15 |  | 2021-02-15 |  |  | Report User Access | API get data user access | IN PROGRES | FIRZA
29 | 2021-02-15 | 2021-02-11 | 2 Day | 2021-02-11 | 2021-02-15 | 1 Day | 2021-02-15 | API SFA & DKDS | SFA | Report User Access | 1). API get data user access | IN REVIEW | FIRZA
[11 empty] | 2). Simpan last access menu untuk mendapatkan jam out | IN REVIEW | FIRZA
[11 empty] | 3). Export xls | IN REVIEW | FIRZA
30 | 2021-02-16 | 2021-02-16 | 1 Day | 2021-02-16 | 2021-02-16 | 1 Day | 2021-02-16 | API SFA & DKDS | SFA | Report Penjualan Inquiry | API get data penjualan dan gross invoice | IN REVIEW | FIRZA
[10 empty] | Report Exception Order Out of Area | 1). API get data outlet yang koordinatnya tidak sama dengan start latitude longitude | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel dan PDF | IN REVIEW | FIRZA
31 | 2021-02-17 | 2021-02-17 | 1 Day | 2021-02-17 | 2021-02-17 | 1 Day | 2021-02-17 | API SFA & DKDS | SFA | Report Crosschecking Cashier vs Salesman per Salesman | 1). API get data transaksi type canvas sampe dengan pembayaran | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
[10 empty] | Pembayaran | Show list dan detail data ar bayar di web | IN REVIEW | FIRZA
[10 empty] | Tagihan | Show list dan detail data tagihan di web | IN REVIEW | FIRZA
[8 empty] | API SFA | BAYAR | - | Error: Setting unknown property: app\\models\\transaction\\ProductSample::sales_code | DONE | DANI
32 | 2021-02-18 | 2021-02-18 | 1 Day | 2021-02-18 | 2021-02-18 | 1 Day | 2021-02-18 | API SFA & DKDS | SFA | Product Sample | Show list dan detail data product sample di web | IN REVIEW | FIRZA
[10 empty] | Delivery Dropping | Show list dan detail data stock dropping di web | IN REVIEW | FIRZA
33 | 2021-02-19 | 2021-02-19 | 1 Day | 2021-02-19 | 2021-02-19 | 1 Day | 2021-02-19 | API SFA & DKDS | SFA | Master Kompetitor Product | Revisi: 1). Error properti code saat create | IN REVIEW | FIRZA
[11 empty] | 2). Revisi show data list and view | IN REVIEW | FIRZA
[10 empty] | Cek Stok | Show list dan detail stok outlet | IN REVIEW | FIRZA
34 | 2021-02-22 | 2021-02-22 | 1 Day | 2021-02-22 | 2021-02-22 | 1 Day | 2021-02-22 | API SFA & DKDS | SFA | Laporan Dinding | Tampilkan ECG, EC route, EC Non Route, Not ECG, Not Visit(Route) | IN REVIEW | FIRZA
[10 empty] | Report Penjualan Inquiry Realisasi | Tampilkan ECS, Gross PPN, Net PPN, Diskon | IN REVIEW | FIRZA
35 | 2021-02-23 | 2021-02-23 | 1 Day | 2021-02-23 | 2021-02-23 | 1 Day | 2021-02-23 | API SFA | TRANSAKSI | - | API kirim data market share ke server SFA | DONE | DANI
|  |  | 2 Day |  | 2021-02-25 |  | 2021-02-25 | API SFA & DKDS | SFA | Report Kompetitor Market Share | API get data transaksi market share | IN PROGRES | FIRZA
36 | 2021-02-25 | 2021-02-25 | 1 Day | 2021-02-25 | 2021-02-25 | 1 Day | 2021-02-25 | API SFA | TRANSAKSI | - | Revisi: 1). Syntax error, unexpected 'class' (T_CLASS), expecting ',' or ';' | DONE | DANI
[11 empty] | 2). Error Exception: data yang dikirim bisa lebih dari 1 object array | DONE | DANI
[11 empty] | API kirim data activity kompetitor | DONE | DANI
[11 empty] | API kirim data new activity | DONE | DANI
|  | 2021-02-23 | 2 Day | 2021-02-23 |  |  |  | API SFA & DKDS | SFA | Report Kompetitor Market Share | 1). API get data transaksi market share | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
37 | 2021-02-26 | 2021-02-26 | 1 Day | 2021-02-26 | 2021-02-26 | 1 Day | 2021-02-26 | API SFA | TRANSAKSI | - | Revisi: 1). Error create transaction kompetitor new activity: outlet code should contain at most 7 characters. | DONE | DANI
[11 empty] | 2). Error Exception "," message ":" Undefined property: stdClass::$code | DONE | DANI
[8 empty] | API SFA & DKDS | SFA | Report Kompetitor Activity | 1). API get data kompetitor activity | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
38 | 2021-03-02 | 2021-03-02 | 1 Day | 2021-03-02 | 2021-03-02 | 1 Day | 2021-03-02 | API SFA | TRANSAKSI | - | API kirim data availability ke server SFA | DONE | DANI
[8 empty] | API SFA & DKDS | SFA | Report Kompetitor New Product | 1). API get data transaksi new product kompetitor | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
[10 empty] | Report Kompetitor Availability | 1). API get data transaksi availability | IN REVIEW | FIRZA
[11 empty] | 2). Export to excel | IN REVIEW | FIRZA
39 | 2021-03-03 | 2021-03-03 | 1 Day | 2021-03-03 | 2021-03-03 | 1 Day | 2021-03-03 | API SFA & DKDS | SFA | Master Kompetitor Sub Brand | Revisi: 1). Tampilkan kode dan nama brand di view | DONE | FIRZA
[11 empty] | 2). Subbrand kalau sudah digunakan di produk kompetitor, tidak boleh dihapus | DONE | FIRZA
[10 empty] | Master Kompetitor Brand | Revisi: 1). Brand kalau sudah digunakan di subbrand, tidak boleh dihapus | DONE | FIRZA
[10 empty] | Master Kompetitor Product | Revisi: 1). Kolom product jangan di limit 7 character supaya bisa search by name | DONE | FIRZA
[11 empty] | 2). Product kompetitor tidak boleh sama dengan menggunakan brand yang sama | DONE | FIRZA
[11 empty] | 3). Saat update kolom brand, subbrand dan flavour, flag status active hilang | DONE | FIRZA
[11 empty] | 4). Status active jadikan true pada saat create | DONE | FIRZA
[11 empty] | 5). Primary key bukan di pcode, tapi di product kompetitor. 1 pcode DKDS bisa dimappingkan utk beberapa product kompetitor | DONE | FIRZA
[11 empty] | 6). Tampilkan brand, subbrand dan flavour di list | DONE | FIRZA
[11 empty] | 7). Kolom weight kasi keterangan satuan (in gram) | DONE | FIRZA
[10 empty] | Master Kompetitor Activity | Revisi: 1). Tampilkan kolom brand di view | DONE | FIRZA
[10 empty] | Report Monitoring Credit Limit | Revisi: 1). Jika kolom region di clear, trigger clear pada kolom titik dan distributor | DONE | FIRZA
[11 empty] | 2). Beri keterangan data tidak ditemukan jika tidak ada data di export to excel | DONE | FIRZA
[11 empty] | 3). Tambahkan user cetak dan tanggal cetak di list dan export to excel | DONE | FIRZA
[8 empty] | API SFA | TRANSAKSI | - | 1). API create transaksi availability detail | DONE | DANI
[11 empty] | 2). Simpan foto di header | DONE | DANI
40 | 2021-03-04 | 2021-03-04 | 1 Day | 2021-03-04 | 2021-03-04 | 1 Day | 2021-03-04 | API SFA | TRANSAKSI | - | Revisi: 1). Error pada saat create header availability | DONE | DANI
[11 empty] | 2). Error numeric value out of range on column created_at updated_at | DONE | DANI
[8 empty] | API SFA & DKDS | SFA | Report Kompetitor Availability | Revisi: 1). API get data availability dan detail availability | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Revisi data export to excel | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Target vs Realization | Revisi: 1). Jika kolom region di clear, trigger clear pada kolom titik dan distributor | IN REVIEW | FIRZA/MONICA
[11 empty] | 2).Revisi nama kolom achieve | IN REVIEW | FIRZA/MONICA
[8 empty] | DKDS |  | ALL REPORT | Beri keterangan data tidak ditemukan di export to excel jika data kosong | IN REVIEW | FIRZA/MONICA
[11 empty] | Beri tanggal cetak dan user cetak di export to excel | IN REVIEW | FIRZA/MONICA
[8 empty] | API SFA | TRANSAKSI | - | Error Save: NO SJ SHOULD CONTAIN AT MOST 16 CHARACTERS. | DONE | DANI
41 | 2021-03-05 | 2021-03-05 | 1 Day | 2021-03-05 | 2021-03-05 | 1 Day | 2021-03-05 | API SFA | - | - | 1). Setup composer untuk php7 | DONE | -
[11 empty] | 2). Install, Setup mongo DB | DONE | -
42 | 2021-03-08 | 2021-03-08 | 3 Day | 2021-03-08 | 2021-03-10 | 1 Day | 2021-03-10 | API SFA & DKDS | SFA | Real Order | Simpan sales type dan gudang code dari API | IN REVIEW | FIRZA/MONICA
[11 empty] | Post multiple: 1). List salesman, outlet, real order, distributor | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Render detail real order | IN REVIEW | FIRZA/MONICA
[11 empty] | 3). Check uncheck multiple post | IN REVIEW | FIRZA/MONICA
[11 empty] | 4). Post multiple RO | IN PROGRES | FIRZA/MONICA
43 | 2021-03-09 | 2021-03-08 | 3 Day | 2021-03-08 | 2021-03-10 | 1 Day | 2021-03-10 | API SFA & DKDS | SFA | Real Order | Post multiple RO | IN PROGRES | FIRZA/MONICA
44 | 2021-03-10 | 2021-03-08 | 3 Day | 2021-03-08 | 2021-03-10 | 1 Day | 2021-03-10 | API SFA & DKDS | SFA | Real Order | Post multiple RO | IN REVIEW | FIRZA/MONICA
|  | 2021-03-10 | 1 Day | 2021-03-10 | 2021-03-10 |  | 2021-03-10 | API SFA | TRANSAKSI | - | Setting unknown property: app\\models\\transaction\\CostSalesman::sales_code | DONE | DANI
[11 empty] | API send data setoran bank ke server SFA | DONE | DANI
45 | 2021-03-12 | 2021-03-12 | 1 Day | 2021-03-12 | 2021-03-12 | 1 Day | 2021-03-12 | API SFA & DKDS | SFA | Report KM Awal - Akhir | Revisi: 1). Hapus region nation dan area | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). revisi query API get POST view dan export | IN REVIEW | FIRZA/MONICA
[10 empty] | Master Kompetitor Product | Revisi: 1). Error array to string conversion pada saat simpan | IN REVIEW | FIRZA/MONICA
[10 empty] | Master Kompetitor Sub Brand | Revisi: 1). Jika ada data dihapus, update status jadi 1, ketika create data baru dengan kode yang sudah dihapus, update status jadi 1 | IN REVIEW | FIRZA/MONICA
[10 empty] | Master Kompetitor Brand | Revisi: 1). Jika ada data dihapus, update status jadi 1, ketika create data baru dengan kode yang sudah dihapus, update status jadi 1 | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Stock Outlet | Revisi: 1). Login sebagai SA Banjarmasin, munculnya data LPD Surabaya (List dan Export) | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Beri keterangan data tidak ditemukan jika tidak ada data di export to excel | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Generator Code | Filter user ditampilkan di export excel dan pdf | IN REVIEW | FIRZA/MONICA
[10 empty] | All Report | Tambahkan user cetak dan jam cetak di semua export pdf | IN REVIEW | FIRZA/MONICA
[10 empty] | Real Order | Revisi: 1). Tampilkan No.RO DKDS setelah post, dan kasi link otomatis ngarah ke RO DKDS | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Tgl PO kalau type transaksi CANVAS, ngikutin tanggal transaksi SFA | IN REVIEW | FIRZA/MONICA
46 | 2021-03-15 | 2021-03-15 | 1 Day | 2021-03-15 | 2021-03-15 | 1 Day | 2021-03-15 | API SFA & DKDS | SFA | Report Stock Cabang | Revisi: 1). Tambahkan hierarki region, tiitk dan distributor | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Tambahkan batasan hierarki sesuai user login | IN REVIEW | FIRZA/MONICA
[11 empty] | 3). Export to excel tambahkan hierarki di header | IN REVIEW | FIRZA/MONICA
[11 empty] | 4). Tambah export to PDF | IN REVIEW | FIRZA/MONICA
[11 empty] | 5). Di list view kolom outlet salah data | IN REVIEW | FIRZA/MONICA
[11 empty] | 6). 1 outlet has to many dengan data produk | IN REVIEW | FIRZA/MONICA
[10 empty] | Real Order | Revisi: 1). Untuk salesman type canvas, gudang codenya ngikuti gudang salesman | IN REVIEW | FIRZA/MONICA
[10 empty] | Master Kompetitor Product | Revisi: 1). Tambahkan satuan In Gram di form create dan view | IN REVIEW | FIRZA/MONICA
[10 empty] | Master Kompetitor Activity | Revisi: 1). Nama label kode dan name activity salah | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Analisa Kunjungan Salesman | Revisi: 1). Data diurutkan sesuai tanggal transaksinya (ascending), kemudian kasih hari nya juga, <<hari>>,<<tanggal>> <<jumlah salesman yg transaksi hari itu>> | IN REVIEW | FIRZA/MONICA
[8 empty] | API DKDS | - | - | Revisi save log transport tracking | DONE | KARIM
47 | 2021-03-16 | 2021-03-16 | 1 Day | 2021-03-16 | 2021-03-16 | 1 Day | 2021-03-16 | API SFA & DKDS | SFA | Report Analisa Kunjungan Salesman | Revisi: 1). Data route sales muncul ketika sudah start visit | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Call plan di dapat dari jumlah rute outlet hari ini. Outlet non rute tidak dihitung | IN REVIEW | FIRZA/MONICA
[11 empty] | 3). Revisi nilai order, ipt, actual plan, ecg, ecs, ipts, iptg dll | IN REVIEW | FIRZA/MONICA
48 | 2021-03-17 | 2021-03-17 | 1 Day | 2021-03-17 | 2021-03-17 | 1 Day | 2021-03-17 | API SFA & DKDS | SFA | All Report | Beri batasan hierarki untuk user SA/TSS/ HOR/HOS/SA HOR/OWNER/OM/SA HOS | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Dropping | Revisi: 1). Tambahkan hierarki region, titik dan distributor di list view dan export to excel | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Stock Outlet | Revisi: 1). Login user SA GT Banjarmasin, filter titik mucul semua, harusnya cuma titik banjarmasin | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Kolom distributor kosong pada saat export to excel | IN REVIEW | FIRZA/MONICA
[11 empty] | 3). Export to pdf internal server error | IN REVIEW | FIRZA/MONICA
[10 empty] | Report KM Awal - Akhir | Revisi: 1). Button export to excel dan pdf samakan dengan model report yang lain | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Gambar di kolom foto km awal dan km akhir tidak muncul | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Generator Code | Revisi: 1). Button export to excel dan pdf samakan dengan model report yang lain | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Unfullfillment | Revisi: 1). Tampilan data salesman dan outlet di rapikan (di ratakan dengan kolom header) | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Reason pause tidak usah ditampilkan, hanya reason not buy dan not visit saja | IN REVIEW | FIRZA/MONICA
49 | 2021-03-18 | 2021-03-18 | 1 Day | 2021-03-18 | 2021-03-18 | 1 Day | 2021-03-18 | API SFA | - | - | Revisi: 1). Tambahkan pengecekan device id dan user id ketika send data ke server SFA | DONE | DANI
[11 empty] | 2). Service firebase untuk push notification data sharing inbox | DONE | DANI
[8 empty] | API SFA & DKDS | SFA | Master Kompetitor Product | Revisi: 1). Primary key bukan di pcode, tapi di pcode_kompetitor | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Analisa Kunjungan Salesman | Revisi: 1). Waktu tempuh ditambahkan selisih harinya juga | IN REVIEW | FIRZA/MONICA
50 | 2021-03-19 | 2021-03-19 | 1 Day | 2021-03-19 | 2021-03-19 | 1 Day | 2021-03-19 | API SFA | - | - | Revisi: 1). Tambah pengecekan kalau data inbox sudah dibaca, beri keterangan Data not found | DONE | DANI
[11 empty] | Create DB log_sfa on mongoDB | DONE | -
[11 empty] | Create collection: user_access (digunakan untuk simpan data user akses menu SFA) | DONE | -
[11 empty] | Install and Config mongoDB on server API 10.6.11.131 (Centos OS) | DONE | -
|  |  | 3 Day |  | 2021-03-24 |  | 2021-03-24 |  |  |  | Intergrasi API SFA dengan mongoDB | IN PROGRES | -
51 | 2021-03-23 | 2021-03-19 | 3 Day | 2021-03-19 | 2021-03-24 | 1 Day | 2021-03-24 | API SFA | - | - | Intergrasi API SFA dengan mongoDB | IN PROGRES | -
[11 empty] | Install, Config FastAPI in local DB | DONE | -
|  | 2021-03-23 | 1 Day | 2021-03-23 | 2021-03-23 |  | 2021-03-23 |  |  |  | Tambah kolom latitude dan longitude di table transaction_rorder | DONE | GALIH
52 | 2021-03-24 | 2021-03-19 | 3 Day | 2021-03-19 | 2021-03-24 | 1 Day | 2021-03-24 | API SFA | - | - | Mencari cara menjadikan date to int dan string tot time di mongoDB menggunakan FASTAPI | DONE | -
[11 empty] | Mencari cara untuk menyimpan ip clint di mongoDB menggunakan fastAPI pyton | DONE | -
[11 empty] | Query count mongoDB untuk mencari urutan | DONE | -
|  | 2021-03-24 | 2 Day | 2021-03-24 | 2021-03-25 |  | 2021-03-25 |  |  |  | Mencari cara untuk mengetahui kapan terakhir kali user mengakses menu (hari dan jamnya) | IN PROGRES | -
53 | 2021-03-25 | 2021-03-24 | 2 Day | 2021-03-24 | 2021-03-25 | 1 Day | 2021-03-25 | API SFA | - | - | Mencari cara untuk mengetahui kapan terakhir kali user mengakses menu (hari dan jamnya) | DONE | -
|  | 2021-03-25 | 1 Day | 2021-03-25 | [6 empty] | Setting CORS (Cross Origin Resource Sharing) untuk cross domain | DONE | -
[8 empty] | DKDS | SFA | ALL MENU SFA | Arahkan logs user access ke API LOG SFA dan simpan data ke DB Mongo | IN REVIEW | FIRZA/MONICA
54 | 2021-03-26 | 2021-03-26 | 1 Day | 2021-03-26 | 2021-03-26 | 1 Day | 2021-03-26 | API SFA | - | - | Create repository untuk API LOG SFA | DONE | -
[11 empty] | Tambahkan file docker ke dalam projek | DONE | -
[11 empty] | Tambahkan environtment ke dalam projek | DONE | -
|  |  | 3 Day |  | 2021-03-30 |  | 2021-03-30 |  |  |  | Implementasi mongoclient untuk manipulasi data | IN PROGRES | -
55 | 2021-03-29 | 2021-03-26 | 3 Day | 2021-03-26 | 2021-03-30 | 1 Day | 2021-03-30 | API SFA | - | - | Implementasi mongoclient untuk manipulasi data | PENDING | -
[11 empty] | Implementasi mongoengine untuk manipulasi data | IN PROGRES | -
56 | 2021-03-30 | 2021-03-26 | 3 Day | 2021-03-26 | 2021-03-30 | 1 Day | 2021-03-30 | API SFA | - | - | Implementasi mongoengine untuk manipulasi data | DONE | -
|  | 2021-03-30 | 1 Day | 2021-03-30 |  |  |  | SFA | - | - | Tambah index di semua table transaction di DB SFA | DONE | -
[8 empty] | API SFA & DKDS | SFA | Report User Access | Revisi: 1). Get data dari API LOG SFA (mongo DB) | IN REVIEW | FIRZA/MONICA
57 | 2121-03-31 | 2121-03-31 | 1 Day | 2121-03-31 | 2021-03-31 | 1 Day | 2021-03-31 | API SFA | - | - | Add maxlengt outlet_code di semua table dan model | DONE | DANI
[9 empty] | - | - | Tambahkan filter distributor code saat query loc_outlet di semua query report | DONE | FIRZA/MONICA
[9 empty] | - | - | Tambah kolom date setoran di table setoran_bank | DONE | DANI
[9 empty] | - | - | Tambah kolom activity name di transaction_kompetitor_activity | DONE | DANI
[8 empty] | API SFA & DKDS | SFA | Report Kompetitor Activity | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Kompetitor Availability | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Kompetitor New Product | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Kompetitor Market Share | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Transaksi Sample | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Collection | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Tambahkan kolom amount cndn, kemudian untuk type cndn ditampilkan di kolom remark cndn | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Crosschecking Cashier vs Salesman per Salesman | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Filter salesman tambahkan keterangan type operasi salesman | IN REVIEW | FIRZA/MONICA
|  |  | 2 Day |  | 2021-04-01 |  | 2021-04-01 |  |  |  | 3). Data setoran tidak muncul, data setoran bank ditampilkan kalau sudah di approve oleh SA/AR | IN PROGRES | FIRZA/MONICA
[11 empty] | 4). Tambahkan kolom buat nampilin foto transfer | IN PROGRES | FIRZA/MONICA
58 | 2021-04-01 | 2021-03-31 | 2 Day | 2021-03-31 | 2021-04-01 | 1 Day | 2021-04-01 | API SFA & DKDS | SFA | Report Crosschecking Cashier vs Salesman per Salesman | Revisi: 1). Data setoran tidak muncul, data setoran bank ditampilkan kalau sudah di approve oleh SA/AR | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Tambahkan kolom buat nampilin foto transfer | IN REVIEW | FIRZA/MONICA
|  | 2021-04-01 | 1 Day | 2021-04-01 | [5 empty] | Report Return Detail | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Return Summary | Revisi: 1). Tambahkan export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Kompetitor Activity | Revisi: 1). Kolom kode dan nama adalah brand kompetitor, sedangkan kolom produk dan nama produk adalah produk kompetitor | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Tambahkan kolom tanggal transaksi | IN REVIEW | FIRZA/MONICA
|  |  | 2 Day |  | 2021-04-05 |  | 2021-04-05 |  |  | Real Order | Kirim data real order dari server SFA ke DB DKDS Distributor | IN PROGRES | FIRZA/MONICA
59 | 2021-04-05 | 2021-04-01 | 2 Day | 2021-04-01 | 2021-04-05 | 1 Day | 2021-04-05 | API SFA & DKDS | SFA | Real Order | Kirim data real order dari server SFA ke DB DKDS Distributor | IN REVIEW | FIRZA/MONICA
[11 empty] | Limit multiple post (10 records) | IN REVIEW | FIRZA/MONICA
|  | 2021-04-05 |  | 2021-04-05 | 2021-04-06 |  | 2021-04-06 | API LOG SFA | - | - | Object data to array from mongo object | IN PROGRES | -
60 | 2021-04-06 | 2021-04-05 | 2 Day | 2021-04-05 | 2021-04-06 | 1 Day | 2021-04-06 | API LOG SFA | - | - | Object data to array from mongo object | DONE | -
[11 empty] | Revisi urutan ketika akses menu yang sama | DONE | -
[11 empty] | Revisi timestamps untuk created_at dan updated_at | DONE | -
|  | 2021-04-06 | 1 Day | 2021-04-06 |  |  |  | API LOG SFA & DKDS | SFA | ALL REPORT | Revisi create log user access | DONE | FIRZA/MONICA
[10 empty] | Report User Access | View dan export to excel get data from API mongo | DONE | FIRZA/MONICA
61 | 2021-04-07 | 2021-04-07 | 1 Day | 2021-04-07 | 2021-04-07 | 1 Day | 2021-04-07 | API SFA & DKDS | SFA | Approval Setoran Bank | API get data setoran bank, view list | IN REVIEW | FIRZA/MONICA
|  |  | 2 Day |  | 2021-04-08 |  | 2021-04-08 |  |  |  | Approval setoran bank | IN PROGRES | FIRZA/MONICA
62 | 2021-04-08 | 2021-04-07 | 2 Day | 2021-04-07 | 2021-04-08 | 1 Day | 2021-04-08 | API SFA & DKDS | SFA | Approval Setoran Bank | Tambah kolom outlet_code, id_bayar, nama bank | DONE | DANI
[11 empty] | Approval setoran bank | IN REVIEW | FIRZA/MONICA
|  | 2021-04-08 | 1 Day | 2021-04-08 |  |  |  | API SFA | - | - | Add kolom nation, region, area, titik dan distributor name di table transaksi_rorder, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table transaksi_kompetitor_new_product, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table transaksi_kompetitor_activity, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table transaksi_kompetitor_availability, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table transaksi_kompetitor_market_share, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table transaksi_absent, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table transaksi_check_stock, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table retur_product, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table product_sample, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table stock_dropping, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Add kolom nation, region, area, titik dan distributor name di table setoran_bank, model, dan simpan pada saat send data dari APK | DONE | FIRZA/MONICA
[11 empty] | Built function untuk mendapatkan data hierarki dari server DKDS untuk disimpan di table transaksi SFA secara otomatis | DONE | FIRZA/MONICA
63 | 2021-04-09 | 2021-04-09 | 1/2 Day | 2021-04-09 | 2021-04-09 | 1/2 Day | 2021-04-09 | API LOG SFA | - | - | Built function return response | DONE | -
[8 empty] | API LOG SFA, API SFA & DKDS | SFA | Master Kompetitor Activity | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Master Kompetitor Brand | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Master Kompetitor Sub Brand | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Master Kompetitor Product | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Master Growth | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Master Setoran Bank | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Master Cost Salesman | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
64 | 2021-04-12 | 2021-04-12 | 1 Day | 2021-04-12 | 2021-04-12 | 1 Day | 2021-04-12 | API LOG SFA, API SFA & DKDS | SFA | Master TOP | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Master Type Reason | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Master Reason | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Sharing Inbox | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Global Parameter | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[10 empty] | Menu | Add logs pada saat create, uppdate, delete | DONE | FIRZA/MONICA
[8 empty] | API SFA | - | - | API untuk ambil data master kompetiror brand, subbrand, product kategori dan flavour (digunakan di smmdk mobile) | DONE | EFENDI
[11 empty] | Tambah sales_code dan sales_name di loc_outlet_noo | DONE | FIRZA
[8 empty] | API LOG SFA |  |  | Custom docker file, mongo authentication and environment file | DONE | EKO
65 | 2021-04-13 | 2021-04-13 | 1 Day | 2021-04-13 | 2021-04-13 | 1 Day | 2021-04-13 | API SFA & DKDS | SFA | Approval Setoran Bank | 1). API Get data setting user approve from DKDS | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Request and send mail approval | IN REVIEW | FIRZA/MONICA
|  |  | 2 Day |  | 2021-04-14 |  | 2021-04-14 |  |  |  | 3). API Build function user approval (model hierarki) | IN PROGRES | FIRZA/MONICA
66 | 2021-04-14 | 2021-04-13 | 2 Day | 2021-04-13 | 2021-04-14 | 1 Day | 2021-04-14 | API SFA & DKDS | SFA | Approval Setoran Bank | 1). API Build function user approval (model hierarki) | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Halaman approval untuk user, proses approval dan rejected | IN REVIEW | FIRZA/MONICA
67 | 2021-04-15 | 2021-04-15 | 1 Day | 2021-04-15 | 2021-04-15 | 1 Day | 2021-04-15 | API LOG SFA | - | - | Config authenticate untuk akses DB | DONE | -
[11 empty] | Problem mongodb:27017: [Errno -2] Name or service not known, Timeout: 30s, Topology Description: TopologyDescription id: 6077e999946100f98919f886 | IN PROGRES | -
68 | 2021-04-16 | 2021-04-16 | 1 Day | 2021-04-16 | 2021-04-16 | 1 Day | 2021-04-16 | API SFA | - | - | Firebase id ambil dari table profile_sfa_register, digunakan untuk notifikasi sharing inbox | DONE | DANI
[8 empty] | API SFA & DKDS | SFA | Report Dropping | Tambah export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Cost Salesman | Tambah export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Transaksi TO | Tambah export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Target vs Realization | Tambah export to PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Monitoring Credit Limit | Tambah export to PDF | IN REVIEW | FIRZA/MONICA
[8 empty] | API LOG SFA | - | - | Problem mongodb:27017: [Errno -2] Name or service not known, Timeout: 30s, Topology Description: TopologyDescription id: 6077e999946100f98919f886 | DONE | -
69 | 2021-04-19 | 2021-04-19 | 1 Day | 2021-04-19 | 2021-04-19 | 1 Day | 2021-04-19 | API LOG SFA | - | - | Implementasi docker untuk membuat image dan container mongoDB API Log SFA | DONE | FIRZA/MONICA
[11 empty] | Simpan longitude, latitude dan battery salesman | DONE | FIRZA/MONICA
[8 empty] | API SFA |  |  | Create connection untuk simpan data log location ke db mongo | DONE | FIRZA/MONICA
70 | 2021-04-20 | 2021-04-20 | 1 Day | 2021-04-20 | 2021-04-20 | 1 Day | 2021-04-20 | API LOG SFA | - | - | Query aggregation, merubah timestamp mongodb ke format date | DONE | FIRZA
[8 empty] | API SFA & DKDS | SFA | Report Unfullfillment | Revisi: 1). Error view (distributor_code not found) | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Di export to excel dan export pdf, reason pause di hilangkan | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Monitoring Credit Limit | Revisi: Tulisan cetak hanya ada di export excel dan export pdf (di view tidak perlu) | IN REVIEW | FIRZA/MONICA
[10 empty] | Report KM Awal - Akhir | Revisi: 1). Salah filter pada saat query export to pdf dan excel | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Gambar belum muncul di export PDF | IN REVIEW | FIRZA/MONICA
[10 empty] | ALL REPORT | Revisi: 1). Print PDF jika data lebih dari 1 lembar, tampilanya ke tumpuk | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Filter region di clear, semua filter hierarki harusnya ke clear | IN REVIEW | FIRZA/MONICA
71 | 2021-04-21 | 2021-04-21 | 1 Day | 2021-04-21 | 2021-04-21 | 1 Day | 2021-04-21 | API LOG SFA | - | - | Hilangkan mapper di module user access | DONE | -
[11 empty] | API untuk ambil data logs location, digunakan di menu tracker | DONE | -
[11 empty] | Routing logs location dan user access jadikan satu per module | DONE | -
[8 empty] | API SFA & DKDS | SFA | Tracker | Data log location ambil dari DB mongo (lewat API Log) | IN REVIEW | FIRZA/MONICA
[10 empty] | Master Kompetitor Product | Kode produk kompetitor boleh sama untuk brand yang berbeda, tetapi tidak boleh sama untuk brand yang sama | IN REVIEW | FIRZA/MONICA
72 | 2021-04-22 | 2021-04-22 | 1 Day | 2021-04-22 | 2021-04-22 | 1 Day | 2021-04-22 | API SFA & DKDS | SFA | Report KM Awal - Akhir | Revisi: error get attribute pada saat export excel | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Penjualan Inquiry Realisasi | Tambah export to excel dan pdf | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Dinding | Tambah export to excel dan pdf | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Data Control | Tambah export to PDF | IN REVIEW | FIRZA/MONICA
73 | 2021-04-23 | 2021-04-23 | 1 Day | 2021-04-23 | 2021-04-23 | 1 Day | 2021-04-23 | API LOG SFA | - | - | Implementasi data model mongoDB (Embed Field) untuk mengurangi resource / ukuran / size data | DONE | -
74 | 2021-04-26 | 2021-04-26 | 1 Day | 2021-04-26 | 2021-04-26 | 1 Day | 2021-04-26 | API SFA & DKDS | SFA | Report Top N | 1). Export pdf dan export excel untuk type product by value | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Export pdf dan export excel untuk type customer by qty | IN REVIEW | FIRZA/MONICA
[11 empty] | 3). Export pdf dan export excel untuk type product by qty | IN REVIEW | FIRZA/MONICA
[11 empty] | 4). Export pdf dan export excel untuk type customer by value | IN REVIEW | FIRZA/MONICA
75 | 2021-04-27 | 2021-04-27 | 1 Day | 2021-04-27 | 2021-04-27 | 1 Day | 2021-04-27 | API SFA & DKDS | SFA | Report Top N | 1). Error load detail customer product by qty (error division by zero) | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Error load detail product customer by qty (error division by zero) | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Collection | 1). Kolom remark CNDN kosong (periode 01-2021-04-2021) | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Problem No.Doc ke parsing ke format excel (mencari cara agar kebaca text biasa) | IN REVIEW | FIRZA/MONICA
76 | 2021-04-28 | 2021-04-28 | 1 Day | 2021-04-28 | 2021-04-28 | 1 Day | 2021-04-28 | API SFA & DKDS | SFA | Report Dropping | Merapikan kolom E, F di export excel | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Collection | No. Doc selalu ke parsing menjadi seperti ini 2,02104E+11 | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Transaksi TO | No. Order selalu ke parsing menjadi seperti ini 2,02104E+11 | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Unfullfillment | Tanggal route masih salah, harusnya ambil date pada saat start visit | IN REVIEW | FIRZA/MONICA
77 | 2021-04-29 | 2021-04-29 | 1 Day | 2021-04-29 | 2021-04-29 | 1 Day | 2021-04-29 | API SFA & DKDS | SFA | Report Transaksi TO | 1). Tambahkan filter hierarki | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Hapus kolom region, titik dan distributor di list view, export excel dan pdf | IN REVIEW | FIRZA/MONICA
[11 empty] | 3). Tampilkan hierarki di header (list view, export excel dan pdf) | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Penjualan Inquiry | 1). Tambahkan filter hierarki | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Hapus kolom region, titik dan distributor di list view | IN REVIEW | FIRZA/MONICA
[10 empty] | Sharing Inbox | Pada saat create, data inbox langsung dikirim ke user yang terdaftar | DONE | DANI
[8 empty] | API SFA | - | - | ERROR CREATE TRANSACTION KOMPETITOR NEW ACTIVITY: PRODUCT CODE SHOULD CONTAIN AT MOST 7 CHARACTERS | DONE | DANI
78 | 2021-04-30 | 2021-04-30 | 1 Day | 2021-04-30 | 2021-04-30 | 1 Day | 2021-04-30 | API SFA | - | - | Tambahkan date transaction di transcation cost salesman | DONE | DANI
79 | 2021-05-03 | 2021-05-03 | 1 Day | 2021-05-03 | 2021-05-03 | 1 Day | 2021-05-03 | API SFA & DKDS | SFA | Report Cost Salesman | 1). Tampilkan tanggal transaksi di list, export pdf dan excel | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Bugfix header export pdf | IN REVIEW | FIRZA/MONICA
[11 empty] | 3). Tampilkan hierarki di header (list view, export excel dan pdf) | IN REVIEW | FIRZA/MONICA
[11 empty] | 4). Bugfix filter tgl 19.04-19.04 data tidak muncul | IN REVIEW | FIRZA/MONICA
[11 empty] | 5). Hapus kolom hierarki di list view, excel dan pdf | IN REVIEW | FIRZA/MONICA
[10 empty] | Master Kompetitor Product | 1). Field sub brand kosong apabila create error / pada saat ke halaman edit | IN REVIEW | FIRZA/MONICA
[11 empty] | 2). Error array to convertion pada saat create | IN REVIEW | FIRZA/MONICA
[10 empty] | Real Order | 1). Tambahkan kolom id_bayar di table transaksi_rorder | DONE | GALIH
[11 empty] | 2). Tambahkan proses simpan ke AR Bayar untuk transaksi canvas | DONE | GALIH
80 | 2021-05-04 | 2021-05-04 | 1 Day | 2021-05-04 | 2021-05-04 | 1 Day | 2021-05-04 | API SFA & DKDS | SFA | Real Order | Bugfix post RO to DKDS | IN REVIEW | FIRZA/MONICA
81 | 2021-05-05 | 2021-05-05 | 1 Day | 2021-05-05 | 2021-05-05 | 1 Day | 2021-05-05 | API SFA & DKDS | SFA | Report Stock Outlet | Pas Region dihapus terus input region ulang, nah itu masih muncul semua titik (munculkan sesuai hierarki) | IN REVIEW | FIRZA/MONICA
[10 empty] | All Report | Login sebagai SA/TSS/HOR/SA HOR/HOS/OWNER/OM/SA HOS belum dibatasin aksesnya (untuk all menu report) | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Data Control | Bugfix slug. Error forbidden access saat menggunakan user SA | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Return Summary | Bugfix slug. Error forbidden access saat menggunakan user SA | IN REVIEW | FIRZA/MONICA
[10 empty] | Report Monitoring Daily Sales / Customer | Bugfix slug. Error forbidden access saat menggunakan user SA | IN REVIEW | FIRZA/MONICA
82 | 2021-05-06 | 2021-05-06 | 1 Day | 2021-05-06 | 2021-05-06 | 1 Day | 2021-05-06 | API SFA & DKDS | SFA | Tagihan | Tambahkan yang sudah dibayar dan sisa bayar | IN REVIEW | FIRZA/MONICA
[11 empty] | Jika type tagihan bukan invoice, maka yang ditampilkan adalah retur | IN REVIEW | FIRZA/MONICA
83 | 2021-05-10 | 2021-05-10 | 1 Day | 2021-05-10 | 2021-05-10 | 1 Day | 2021-05-10 | API SFA & DKDS | SFA | Sharing Inbox | Semua filter tidak jalan | IN REVIEW | FIRZA/MONICA
[8 empty] | API SFA | - | - | Revisi API last order (ambil data 1 bulan terakhir) | DONE | GALIH
[11 empty] | Tambahkan parameter date dan salesID | DONE | GALIH
84 | 2021-05-11 | 2021-05-11 | 1 Day | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | API SFA & DKDS | SFA | Master Kompetitor Activity | Bugfix filter created at dan updated at | DONE | -
[10 empty] | Master Kompetitor Brand | Bugfix filter created at dan updated at | DONE | -
[10 empty] | Master Kompetitor Product | Bugfix filter created at dan updated at | DONE | -
[10 empty] | Master Kompetitor Sub Brand | Bugfix filter created at dan updated at | DONE | -